GSIB Board Duties — Reform Roadmap

v2.1 · July 2026 · three views: feasibility, agency, timeline · companion to the Consolidated Board Duty Set (v0.1, illustrative draft)

What this is. All 31 consolidation levers from the 227-statement corpus, presented three ways: by legal feasibility (View 1 — what is easiest), by agency (View 2 — each regulator's work program), and by timeline (View 3 — the sequence, with dependencies). The same levers appear in each view; pick the view that matches your question. Nothing here is adopted policy; “ready” means fully specified and evidence-anchored, not agreed.

The sequencing logic in one paragraph. Single-agency actions go first because they need no coordination and build momentum. The interagency statements phase runs next and includes the one gating item — the General-Part framework statement — which every later instrument cross-references. Joint rulemakings follow, consuming the definitions and templates the statements produced. The structural prize — letting a bank board rely on the parent enterprise framework — comes last, because it only works once consolidated enterprise standards exist to rely on. Two threads run on their own clocks: the independence definition starts early because SEC coordination is the longest pole, and the §956 branch is a principals’ decision that can land any time.

# View 1 — By feasibility (what is legally easiest)

## Tier 1 — Guidance consolidation

Capital planning & stress testing — Separate board capital-action decisions from technical methodology reporting

When: months 0–6   Effect: clarify   Lead: FRB   Instrument: guidance action plus conforming rule note   Status: ready

No coordination needed; guidance action + conforming note.

## Tier 2 — Interagency statements & coordination

Audit committee & independence — Single 'independent director' definition; one audit committee satisfies all regimes

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement plus SEC coordination   Status: ready

Depends on: Independence definition.  Finalizes the Phase 2 definition work into rules/listing-standard cross-refs.

Board self-assessment / effectiveness — Single interagency board-effectiveness assessment.

When: months 6–12   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Joint statement; near-identical source texts.

Director independence (cross-cutting) — Single cross-referenced prudential independence definition.

When: months 6–24   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement   Status: ready

Start early — SEC coordination is the longest pole; finalizes in Phase 3.

Director training — One consolidated director-training program covering all topics.

When: months 9–18   Effect: change   Lead: FRB+OCC+FDIC+FinCEN   Instrument: interagency statement   Status: ready

Statement; BSA module preserves the statutory training pillar.

Insider / affiliate / related-party — Coordinate related-party review processes.

When: months 6–18   Effect: n/a   Lead: FRB+SEC   Instrument: interagency statement   Status: non-target

Coordination only; no consolidation (distinct statutes).

Liquidity risk management — One board liquidity approval satisfies rule and guidance.

When: months 6–15   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Deem-satisfied statement citing the General-Part mechanics.

Risk appetite statement — Interagency risk-appetite template + safe harbor that one board-approved statement satisfies all.

When: months 6–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Template published with the framework statement; safe harbor may need a conforming rule note (Phase 3).

Risk-governance framework / strategy — One enterprise framework approval with an IDI addendum (expanded App. D reliance accommodation)

When: months 9–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement plus rule safe harbor   Status: ready

Depends on: G-Part statement.  Statement + safe harbor now; feeds the Phase 4 structural expansion.

Risk-governance framework / strategy — Single interagency board-effectiveness assessment

When: months 6–12   Effect: codify   Lead: FRB+OCC   Instrument: joint statement   Status: ready

Duplicate lever entry (MVP D7) — same action.

Third-party risk management — Quantitative 'critical activity' threshold for board attention; management approval + aggregate reporting othe…

When: months 9–18   Effect: clarify   Lead: FRB+OCC+FDIC   Instrument: interagency statement   Status: ready

Depends on: Threshold value (principals).  Amends the 2023 interagency guidance; threshold value is a principals decision.

## Tier 3 — Rule harmonization

BSA/AML program — Cross-reference manual to the rule; avoid restating. v2.1: resolve the two unreconciled pending rewrites (2024…

When: months 6–18   Effect: n/a   Lead: FinCEN+FBAs   Instrument: rule apa   Status: non-target

Reconcile the two pending BSA rewrites before layering compounds; then manual cross-references.

CRO / CRE appointment & compensation — Consolidate into Reg YY; OCC incorporates by reference.

When: months 12–27   Effect: clarify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  CRO/CRE rides the same Reg YY amendment cycle.

Credit risk governance — One interagency real-estate-lending standard; fold ACL/credit-review into the risk-committee credit cycle.

When: months 15–30   Effect: change   Lead: FRB+OCC+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  Credit cycle folds into the consolidated committee standard.

Director eligibility & continuity — Single interagency change-in-director notice procedure.

When: months 12–24   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Modest joint rulemaking.

Fiduciary (trust) governance — Permit the §36/Part 363 audit committee to satisfy the fiduciary-audit duty where composition overlaps.

When: months 0–9   Effect: change   Lead: OCC   Instrument: rule apa   Status: ready

Single-agency 12 CFR 9 amendment.

Information security & cybersecurity — One enterprise info-security program approval; joint SEC/banking statement on cyber oversight. v2.1: the 36-ho…

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: joint rulemaking   Status: ready

Depends on: Timeline selection (principals).  Conform four appendices; the incident-timeline choice is a principals decision.

Internal control over financial reporting — SOX 404(b) satisfies FDICIA ICFR by cross-reference; align cycles

When: months 0–12   Effect: change   Lead: FDIC   Instrument: rule amendment(Part 363)   Status: ready

Single-agency Part 363 amendment; start immediately, lands in Phase 2 window.

Operational resilience / business continuity — Fold into the enterprise risk-appetite approval.

When: months 12–24   Effect: codify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-appetite template.  Operational-resilience fold rides the risk-appetite instruments.

Resolution, recovery & contingency funding — Single 'resilience planning' board cycle; shared resolution submission with an IDI annex.

When: months 15–33   Effect: clarify   Lead: FRB+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: G-Part statement.  Joint rulemaking; FDIC annex preserves the distinct resolvability interest.

Risk committee architecture — One risk-committee standard at the consolidated level + streamlined IDI certification

When: months 12–30   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Independence definition.  Joint rulemaking; App. D cross-references Reg YY; certification template from Phase 2.

Risk-governance framework / strategy — Codify SR 12-17 governance content into Reg YY; retire the letter

When: months 15–30   Effect: change   Lead: FRB   Instrument: rule amendment notice and comment   Status: ready

Depends on: G-Part statement.  Notice-and-comment; the declared guidance-to-rule conversion; retires the letter with a logged signal.

## Tier 5 — Vertical rationalization (structural)

cross-cutting (largest structural lever) — Vertical HC/IDI rationalization via expanded reliance accommodation (schema, per mirror pair)

When: months 24–48   Effect: change   Lead: FRB+OCC+FDIC   Instrument: rulemaking possibly statutory   Status: ready

Depends on: Risk-committee standard; Risk-appetite template; Enterprise framework statement.  The structural prize; requires consolidated enterprise standards in force first; statutory at the margin.

## Tier 6 — Retained, open, and non-target items

Consumer compliance (CMS) — Coordinate CMS expectations; CFPB now lightly enforced (2026).

When: months 9–18   Effect: n/a   Lead: FBAs+CFPB   Status: non-target

Coordination item.

Incentive compensation — Finalize one 956 framework or rely on guidance; SEC independence satisfies the prudential element.

When: months 0–48   Effect: n/a   Lead: 6 agencies (principals)   Status: open branch

Open policy branch; either branch slots into Phase 3 mechanics once decided.

Model risk governance — Confirm the Heightened Standards do not re-impose the dropped board duty. v2.1: SR 26-2 and OCC Bulletin 2026-…

Effect: n/a   Status: non-target

No implementation action (retained / documented non-target).

Personal & individual-director liability — Not a consolidation target; documented to show how personal liability compounds the cost of duplicative mandat…

Effect: n/a   Status: non-target

No implementation action (retained / documented non-target).

Safety-and-soundness baseline — Treat as baseline; avoid re-imposing in domain rules.

Effect: n/a   Status: non-target

No implementation action (retained / documented non-target).

Source of strength / charter sanctity — Clarify the interaction for overlapping directors.

Effect: n/a   Status: non-target

No implementation action (retained / documented non-target).

Unique structural duties — Retain; distinct purpose.

Effect: n/a   Status: non-target

No implementation action (retained / documented non-target).

cross-cutting — Recurring meta-duty (approve framework / review annually / receive reports) -> General Part

When: months 6–15   Effect: fill_gap   Lead: Interagency WG   Instrument: varies   Status: ready

THE G-PART STATEMENT: the framework statement each later instrument cross-references. Gating item for Phases 2-4.

# View 2 — By agency (each regulator's work program)

Actions each agency can start alone, then what it must do jointly. An agency reading only its own section sees its complete program.

## FRB  (24 actions)

Can act alone:

Capital planning & stress testing — Separate board capital-action decisions from technical methodology reporting

When: months 0–6   Effect: clarify   Lead: FRB   Instrument: guidance action plus conforming rule note   Status: ready

No coordination needed; guidance action + conforming note.

Risk-governance framework / strategy — Codify SR 12-17 governance content into Reg YY; retire the letter

When: months 15–30   Effect: change   Lead: FRB   Instrument: rule amendment notice and comment   Status: ready

Depends on: G-Part statement.  Notice-and-comment; the declared guidance-to-rule conversion; retires the letter with a logged signal.

Joint actions:

Incentive compensation — Finalize one 956 framework or rely on guidance; SEC independence satisfies the prudential element.

When: months 0–48   Effect: n/a   Lead: 6 agencies (principals)   Status: open branch

Open policy branch; either branch slots into Phase 3 mechanics once decided.

Board self-assessment / effectiveness — Single interagency board-effectiveness assessment.

When: months 6–12   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Joint statement; near-identical source texts.

Director independence (cross-cutting) — Single cross-referenced prudential independence definition.

When: months 6–24   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement   Status: ready

Start early — SEC coordination is the longest pole; finalizes in Phase 3.

Insider / affiliate / related-party — Coordinate related-party review processes.

When: months 6–18   Effect: n/a   Lead: FRB+SEC   Instrument: interagency statement   Status: non-target

Coordination only; no consolidation (distinct statutes).

Liquidity risk management — One board liquidity approval satisfies rule and guidance.

When: months 6–15   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Deem-satisfied statement citing the General-Part mechanics.

Risk appetite statement — Interagency risk-appetite template + safe harbor that one board-approved statement satisfies all.

When: months 6–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Template published with the framework statement; safe harbor may need a conforming rule note (Phase 3).

Risk-governance framework / strategy — Single interagency board-effectiveness assessment

When: months 6–12   Effect: codify   Lead: FRB+OCC   Instrument: joint statement   Status: ready

Duplicate lever entry (MVP D7) — same action.

BSA/AML program — Cross-reference manual to the rule; avoid restating. v2.1: resolve the two unreconciled pending rewrites (2024…

When: months 6–18   Effect: n/a   Lead: FinCEN+FBAs   Instrument: rule apa   Status: non-target

Reconcile the two pending BSA rewrites before layering compounds; then manual cross-references.

cross-cutting — Recurring meta-duty (approve framework / review annually / receive reports) -> General Part

When: months 6–15   Effect: fill_gap   Lead: Interagency WG   Instrument: varies   Status: ready

THE G-PART STATEMENT: the framework statement each later instrument cross-references. Gating item for Phases 2-4.

Director training — One consolidated director-training program covering all topics.

When: months 9–18   Effect: change   Lead: FRB+OCC+FDIC+FinCEN   Instrument: interagency statement   Status: ready

Statement; BSA module preserves the statutory training pillar.

Risk-governance framework / strategy — One enterprise framework approval with an IDI addendum (expanded App. D reliance accommodation)

When: months 9–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement plus rule safe harbor   Status: ready

Depends on: G-Part statement.  Statement + safe harbor now; feeds the Phase 4 structural expansion.

Third-party risk management — Quantitative 'critical activity' threshold for board attention; management approval + aggregate reporting othe…

When: months 9–18   Effect: clarify   Lead: FRB+OCC+FDIC   Instrument: interagency statement   Status: ready

Depends on: Threshold value (principals).  Amends the 2023 interagency guidance; threshold value is a principals decision.

Consumer compliance (CMS) — Coordinate CMS expectations; CFPB now lightly enforced (2026).

When: months 9–18   Effect: n/a   Lead: FBAs+CFPB   Status: non-target

Coordination item.

Audit committee & independence — Single 'independent director' definition; one audit committee satisfies all regimes

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement plus SEC coordination   Status: ready

Depends on: Independence definition.  Finalizes the Phase 2 definition work into rules/listing-standard cross-refs.

CRO / CRE appointment & compensation — Consolidate into Reg YY; OCC incorporates by reference.

When: months 12–27   Effect: clarify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  CRO/CRE rides the same Reg YY amendment cycle.

Director eligibility & continuity — Single interagency change-in-director notice procedure.

When: months 12–24   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Modest joint rulemaking.

Information security & cybersecurity — One enterprise info-security program approval; joint SEC/banking statement on cyber oversight. v2.1: the 36-ho…

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: joint rulemaking   Status: ready

Depends on: Timeline selection (principals).  Conform four appendices; the incident-timeline choice is a principals decision.

Operational resilience / business continuity — Fold into the enterprise risk-appetite approval.

When: months 12–24   Effect: codify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-appetite template.  Operational-resilience fold rides the risk-appetite instruments.

Risk committee architecture — One risk-committee standard at the consolidated level + streamlined IDI certification

When: months 12–30   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Independence definition.  Joint rulemaking; App. D cross-references Reg YY; certification template from Phase 2.

Credit risk governance — One interagency real-estate-lending standard; fold ACL/credit-review into the risk-committee credit cycle.

When: months 15–30   Effect: change   Lead: FRB+OCC+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  Credit cycle folds into the consolidated committee standard.

Resolution, recovery & contingency funding — Single 'resilience planning' board cycle; shared resolution submission with an IDI annex.

When: months 15–33   Effect: clarify   Lead: FRB+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: G-Part statement.  Joint rulemaking; FDIC annex preserves the distinct resolvability interest.

cross-cutting (largest structural lever) — Vertical HC/IDI rationalization via expanded reliance accommodation (schema, per mirror pair)

When: months 24–48   Effect: change   Lead: FRB+OCC+FDIC   Instrument: rulemaking possibly statutory   Status: ready

Depends on: Risk-committee standard; Risk-appetite template; Enterprise framework statement.  The structural prize; requires consolidated enterprise standards in force first; statutory at the margin.

## OCC  (21 actions)

Can act alone:

Fiduciary (trust) governance — Permit the §36/Part 363 audit committee to satisfy the fiduciary-audit duty where composition overlaps.

When: months 0–9   Effect: change   Lead: OCC   Instrument: rule apa   Status: ready

Single-agency 12 CFR 9 amendment.

Joint actions:

Incentive compensation — Finalize one 956 framework or rely on guidance; SEC independence satisfies the prudential element.

When: months 0–48   Effect: n/a   Lead: 6 agencies (principals)   Status: open branch

Open policy branch; either branch slots into Phase 3 mechanics once decided.

Board self-assessment / effectiveness — Single interagency board-effectiveness assessment.

When: months 6–12   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Joint statement; near-identical source texts.

Director independence (cross-cutting) — Single cross-referenced prudential independence definition.

When: months 6–24   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement   Status: ready

Start early — SEC coordination is the longest pole; finalizes in Phase 3.

Liquidity risk management — One board liquidity approval satisfies rule and guidance.

When: months 6–15   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Deem-satisfied statement citing the General-Part mechanics.

Risk appetite statement — Interagency risk-appetite template + safe harbor that one board-approved statement satisfies all.

When: months 6–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Template published with the framework statement; safe harbor may need a conforming rule note (Phase 3).

Risk-governance framework / strategy — Single interagency board-effectiveness assessment

When: months 6–12   Effect: codify   Lead: FRB+OCC   Instrument: joint statement   Status: ready

Duplicate lever entry (MVP D7) — same action.

BSA/AML program — Cross-reference manual to the rule; avoid restating. v2.1: resolve the two unreconciled pending rewrites (2024…

When: months 6–18   Effect: n/a   Lead: FinCEN+FBAs   Instrument: rule apa   Status: non-target

Reconcile the two pending BSA rewrites before layering compounds; then manual cross-references.

cross-cutting — Recurring meta-duty (approve framework / review annually / receive reports) -> General Part

When: months 6–15   Effect: fill_gap   Lead: Interagency WG   Instrument: varies   Status: ready

THE G-PART STATEMENT: the framework statement each later instrument cross-references. Gating item for Phases 2-4.

Director training — One consolidated director-training program covering all topics.

When: months 9–18   Effect: change   Lead: FRB+OCC+FDIC+FinCEN   Instrument: interagency statement   Status: ready

Statement; BSA module preserves the statutory training pillar.

Risk-governance framework / strategy — One enterprise framework approval with an IDI addendum (expanded App. D reliance accommodation)

When: months 9–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement plus rule safe harbor   Status: ready

Depends on: G-Part statement.  Statement + safe harbor now; feeds the Phase 4 structural expansion.

Third-party risk management — Quantitative 'critical activity' threshold for board attention; management approval + aggregate reporting othe…

When: months 9–18   Effect: clarify   Lead: FRB+OCC+FDIC   Instrument: interagency statement   Status: ready

Depends on: Threshold value (principals).  Amends the 2023 interagency guidance; threshold value is a principals decision.

Consumer compliance (CMS) — Coordinate CMS expectations; CFPB now lightly enforced (2026).

When: months 9–18   Effect: n/a   Lead: FBAs+CFPB   Status: non-target

Coordination item.

Audit committee & independence — Single 'independent director' definition; one audit committee satisfies all regimes

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement plus SEC coordination   Status: ready

Depends on: Independence definition.  Finalizes the Phase 2 definition work into rules/listing-standard cross-refs.

CRO / CRE appointment & compensation — Consolidate into Reg YY; OCC incorporates by reference.

When: months 12–27   Effect: clarify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  CRO/CRE rides the same Reg YY amendment cycle.

Director eligibility & continuity — Single interagency change-in-director notice procedure.

When: months 12–24   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Modest joint rulemaking.

Information security & cybersecurity — One enterprise info-security program approval; joint SEC/banking statement on cyber oversight. v2.1: the 36-ho…

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: joint rulemaking   Status: ready

Depends on: Timeline selection (principals).  Conform four appendices; the incident-timeline choice is a principals decision.

Operational resilience / business continuity — Fold into the enterprise risk-appetite approval.

When: months 12–24   Effect: codify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-appetite template.  Operational-resilience fold rides the risk-appetite instruments.

Risk committee architecture — One risk-committee standard at the consolidated level + streamlined IDI certification

When: months 12–30   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Independence definition.  Joint rulemaking; App. D cross-references Reg YY; certification template from Phase 2.

Credit risk governance — One interagency real-estate-lending standard; fold ACL/credit-review into the risk-committee credit cycle.

When: months 15–30   Effect: change   Lead: FRB+OCC+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  Credit cycle folds into the consolidated committee standard.

cross-cutting (largest structural lever) — Vertical HC/IDI rationalization via expanded reliance accommodation (schema, per mirror pair)

When: months 24–48   Effect: change   Lead: FRB+OCC+FDIC   Instrument: rulemaking possibly statutory   Status: ready

Depends on: Risk-committee standard; Risk-appetite template; Enterprise framework statement.  The structural prize; requires consolidated enterprise standards in force first; statutory at the margin.

## FDIC  (13 actions)

Can act alone:

Internal control over financial reporting — SOX 404(b) satisfies FDICIA ICFR by cross-reference; align cycles

When: months 0–12   Effect: change   Lead: FDIC   Instrument: rule amendment(Part 363)   Status: ready

Single-agency Part 363 amendment; start immediately, lands in Phase 2 window.

Joint actions:

Incentive compensation — Finalize one 956 framework or rely on guidance; SEC independence satisfies the prudential element.

When: months 0–48   Effect: n/a   Lead: 6 agencies (principals)   Status: open branch

Open policy branch; either branch slots into Phase 3 mechanics once decided.

Director independence (cross-cutting) — Single cross-referenced prudential independence definition.

When: months 6–24   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement   Status: ready

Start early — SEC coordination is the longest pole; finalizes in Phase 3.

BSA/AML program — Cross-reference manual to the rule; avoid restating. v2.1: resolve the two unreconciled pending rewrites (2024…

When: months 6–18   Effect: n/a   Lead: FinCEN+FBAs   Instrument: rule apa   Status: non-target

Reconcile the two pending BSA rewrites before layering compounds; then manual cross-references.

cross-cutting — Recurring meta-duty (approve framework / review annually / receive reports) -> General Part

When: months 6–15   Effect: fill_gap   Lead: Interagency WG   Instrument: varies   Status: ready

THE G-PART STATEMENT: the framework statement each later instrument cross-references. Gating item for Phases 2-4.

Director training — One consolidated director-training program covering all topics.

When: months 9–18   Effect: change   Lead: FRB+OCC+FDIC+FinCEN   Instrument: interagency statement   Status: ready

Statement; BSA module preserves the statutory training pillar.

Third-party risk management — Quantitative 'critical activity' threshold for board attention; management approval + aggregate reporting othe…

When: months 9–18   Effect: clarify   Lead: FRB+OCC+FDIC   Instrument: interagency statement   Status: ready

Depends on: Threshold value (principals).  Amends the 2023 interagency guidance; threshold value is a principals decision.

Consumer compliance (CMS) — Coordinate CMS expectations; CFPB now lightly enforced (2026).

When: months 9–18   Effect: n/a   Lead: FBAs+CFPB   Status: non-target

Coordination item.

Audit committee & independence — Single 'independent director' definition; one audit committee satisfies all regimes

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement plus SEC coordination   Status: ready

Depends on: Independence definition.  Finalizes the Phase 2 definition work into rules/listing-standard cross-refs.

Information security & cybersecurity — One enterprise info-security program approval; joint SEC/banking statement on cyber oversight. v2.1: the 36-ho…

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: joint rulemaking   Status: ready

Depends on: Timeline selection (principals).  Conform four appendices; the incident-timeline choice is a principals decision.

Credit risk governance — One interagency real-estate-lending standard; fold ACL/credit-review into the risk-committee credit cycle.

When: months 15–30   Effect: change   Lead: FRB+OCC+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  Credit cycle folds into the consolidated committee standard.

Resolution, recovery & contingency funding — Single 'resilience planning' board cycle; shared resolution submission with an IDI annex.

When: months 15–33   Effect: clarify   Lead: FRB+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: G-Part statement.  Joint rulemaking; FDIC annex preserves the distinct resolvability interest.

cross-cutting (largest structural lever) — Vertical HC/IDI rationalization via expanded reliance accommodation (schema, per mirror pair)

When: months 24–48   Effect: change   Lead: FRB+OCC+FDIC   Instrument: rulemaking possibly statutory   Status: ready

Depends on: Risk-committee standard; Risk-appetite template; Enterprise framework statement.  The structural prize; requires consolidated enterprise standards in force first; statutory at the margin.

## SEC  (5 actions)

Joint actions:

Incentive compensation — Finalize one 956 framework or rely on guidance; SEC independence satisfies the prudential element.

When: months 0–48   Effect: n/a   Lead: 6 agencies (principals)   Status: open branch

Open policy branch; either branch slots into Phase 3 mechanics once decided.

Director independence (cross-cutting) — Single cross-referenced prudential independence definition.

When: months 6–24   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement   Status: ready

Start early — SEC coordination is the longest pole; finalizes in Phase 3.

Insider / affiliate / related-party — Coordinate related-party review processes.

When: months 6–18   Effect: n/a   Lead: FRB+SEC   Instrument: interagency statement   Status: non-target

Coordination only; no consolidation (distinct statutes).

Audit committee & independence — Single 'independent director' definition; one audit committee satisfies all regimes

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement plus SEC coordination   Status: ready

Depends on: Independence definition.  Finalizes the Phase 2 definition work into rules/listing-standard cross-refs.

Information security & cybersecurity — One enterprise info-security program approval; joint SEC/banking statement on cyber oversight. v2.1: the 36-ho…

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: joint rulemaking   Status: ready

Depends on: Timeline selection (principals).  Conform four appendices; the incident-timeline choice is a principals decision.

## FinCEN  (2 actions)

Joint actions:

BSA/AML program — Cross-reference manual to the rule; avoid restating. v2.1: resolve the two unreconciled pending rewrites (2024…

When: months 6–18   Effect: n/a   Lead: FinCEN+FBAs   Instrument: rule apa   Status: non-target

Reconcile the two pending BSA rewrites before layering compounds; then manual cross-references.

Director training — One consolidated director-training program covering all topics.

When: months 9–18   Effect: change   Lead: FRB+OCC+FDIC+FinCEN   Instrument: interagency statement   Status: ready

Statement; BSA module preserves the statutory training pillar.

## CFPB  (1 actions)

Joint actions:

Consumer compliance (CMS) — Coordinate CMS expectations; CFPB now lightly enforced (2026).

When: months 9–18   Effect: n/a   Lead: FBAs+CFPB   Status: non-target

Coordination item.

# View 3 — By timeline (the sequence and its dependencies)

## Phase 1 — Single-agency actions (months 0–6)

Three agencies act unilaterally; the interagency working group stands up in parallel. Nothing waits on anyone.

Capital planning & stress testing — Separate board capital-action decisions from technical methodology reporting

When: months 0–6   Effect: clarify   Lead: FRB   Instrument: guidance action plus conforming rule note   Status: ready

No coordination needed; guidance action + conforming note.

Fiduciary (trust) governance — Permit the §36/Part 363 audit committee to satisfy the fiduciary-audit duty where composition overlaps.

When: months 0–9   Effect: change   Lead: OCC   Instrument: rule apa   Status: ready

Single-agency 12 CFR 9 amendment.

Internal control over financial reporting — SOX 404(b) satisfies FDICIA ICFR by cross-reference; align cycles

When: months 0–12   Effect: change   Lead: FDIC   Instrument: rule amendment(Part 363)   Status: ready

Single-agency Part 363 amendment; start immediately, lands in Phase 2 window.

## Phase 2 — Interagency statements & safe harbors (months 6–18)

The gating item lands here: the General-Part framework statement, which every later instrument cross-references. Statements, templates, and safe harbors that need no rule text.

Board self-assessment / effectiveness — Single interagency board-effectiveness assessment.

When: months 6–12   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Joint statement; near-identical source texts.

Risk-governance framework / strategy — Single interagency board-effectiveness assessment

When: months 6–12   Effect: codify   Lead: FRB+OCC   Instrument: joint statement   Status: ready

Duplicate lever entry (MVP D7) — same action.

Liquidity risk management — One board liquidity approval satisfies rule and guidance.

When: months 6–15   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Deem-satisfied statement citing the General-Part mechanics.

cross-cutting — Recurring meta-duty (approve framework / review annually / receive reports) -> General Part

When: months 6–15   Effect: fill_gap   Lead: Interagency WG   Instrument: varies   Status: ready

THE G-PART STATEMENT: the framework statement each later instrument cross-references. Gating item for Phases 2-4.

Insider / affiliate / related-party — Coordinate related-party review processes.

When: months 6–18   Effect: n/a   Lead: FRB+SEC   Instrument: interagency statement   Status: non-target

Coordination only; no consolidation (distinct statutes).

Risk appetite statement — Interagency risk-appetite template + safe harbor that one board-approved statement satisfies all.

When: months 6–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement   Status: ready

Depends on: G-Part statement.  Template published with the framework statement; safe harbor may need a conforming rule note (Phase 3).

BSA/AML program — Cross-reference manual to the rule; avoid restating. v2.1: resolve the two unreconciled pending rewrites (2024…

When: months 6–18   Effect: n/a   Lead: FinCEN+FBAs   Instrument: rule apa   Status: non-target

Reconcile the two pending BSA rewrites before layering compounds; then manual cross-references.

Director independence (cross-cutting) — Single cross-referenced prudential independence definition.

When: months 6–24   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement   Status: ready

Start early — SEC coordination is the longest pole; finalizes in Phase 3.

Director training — One consolidated director-training program covering all topics.

When: months 9–18   Effect: change   Lead: FRB+OCC+FDIC+FinCEN   Instrument: interagency statement   Status: ready

Statement; BSA module preserves the statutory training pillar.

Risk-governance framework / strategy — One enterprise framework approval with an IDI addendum (expanded App. D reliance accommodation)

When: months 9–18   Effect: change   Lead: FRB+OCC   Instrument: interagency statement plus rule safe harbor   Status: ready

Depends on: G-Part statement.  Statement + safe harbor now; feeds the Phase 4 structural expansion.

Third-party risk management — Quantitative 'critical activity' threshold for board attention; management approval + aggregate reporting othe…

When: months 9–18   Effect: clarify   Lead: FRB+OCC+FDIC   Instrument: interagency statement   Status: ready

Depends on: Threshold value (principals).  Amends the 2023 interagency guidance; threshold value is a principals decision.

Consumer compliance (CMS) — Coordinate CMS expectations; CFPB now lightly enforced (2026).

When: months 9–18   Effect: n/a   Lead: FBAs+CFPB   Status: non-target

Coordination item.

## Phase 3 — Joint rulemakings (months 12–30)

Notice-and-comment work consuming Phase 2's definitions and templates. The independence definition (begun in Phase 2 with the SEC) finalizes here.

Director eligibility & continuity — Single interagency change-in-director notice procedure.

When: months 12–24   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Modest joint rulemaking.

Operational resilience / business continuity — Fold into the enterprise risk-appetite approval.

When: months 12–24   Effect: codify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-appetite template.  Operational-resilience fold rides the risk-appetite instruments.

CRO / CRE appointment & compensation — Consolidate into Reg YY; OCC incorporates by reference.

When: months 12–27   Effect: clarify   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  CRO/CRE rides the same Reg YY amendment cycle.

Audit committee & independence — Single 'independent director' definition; one audit committee satisfies all regimes

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: interagency statement plus SEC coordination   Status: ready

Depends on: Independence definition.  Finalizes the Phase 2 definition work into rules/listing-standard cross-refs.

Information security & cybersecurity — One enterprise info-security program approval; joint SEC/banking statement on cyber oversight. v2.1: the 36-ho…

When: months 12–30   Effect: change   Lead: FRB+OCC+FDIC+SEC   Instrument: joint rulemaking   Status: ready

Depends on: Timeline selection (principals).  Conform four appendices; the incident-timeline choice is a principals decision.

Risk committee architecture — One risk-committee standard at the consolidated level + streamlined IDI certification

When: months 12–30   Effect: change   Lead: FRB+OCC   Instrument: joint rulemaking   Status: ready

Depends on: Independence definition.  Joint rulemaking; App. D cross-references Reg YY; certification template from Phase 2.

Credit risk governance — One interagency real-estate-lending standard; fold ACL/credit-review into the risk-committee credit cycle.

When: months 15–30   Effect: change   Lead: FRB+OCC+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: Risk-committee standard.  Credit cycle folds into the consolidated committee standard.

Risk-governance framework / strategy — Codify SR 12-17 governance content into Reg YY; retire the letter

When: months 15–30   Effect: change   Lead: FRB   Instrument: rule amendment notice and comment   Status: ready

Depends on: G-Part statement.  Notice-and-comment; the declared guidance-to-rule conversion; retires the letter with a logged signal.

Resolution, recovery & contingency funding — Single 'resilience planning' board cycle; shared resolution submission with an IDI annex.

When: months 15–33   Effect: clarify   Lead: FRB+FDIC   Instrument: joint rulemaking   Status: ready

Depends on: G-Part statement.  Joint rulemaking; FDIC annex preserves the distinct resolvability interest.

## Phase 4 — Structural: vertical HC/IDI reliance (months 24–48)

The largest lever. Requires the consolidated enterprise standards from Phases 2–3 to be in force; statutory at the margin.

cross-cutting (largest structural lever) — Vertical HC/IDI rationalization via expanded reliance accommodation (schema, per mirror pair)

When: months 24–48   Effect: change   Lead: FRB+OCC+FDIC   Instrument: rulemaking possibly statutory   Status: ready

Depends on: Risk-committee standard; Risk-appetite template; Enterprise framework statement.  The structural prize; requires consolidated enterprise standards in force first; statutory at the margin.

## Principals' decisions (any time)

Items only leadership can decide; each slots into the mechanics above once decided.

Incentive compensation — Finalize one 956 framework or rely on guidance; SEC independence satisfies the prudential element.

When: months 0–48   Effect: n/a   Lead: 6 agencies (principals)   Status: open branch

Open policy branch; either branch slots into Phase 3 mechanics once decided.

# Dependency notes

- The General-Part framework statement gates Phases 2–4: liquidity, risk-appetite, enterprise-framework, SR 12-17 codification, and resilience items all cross-reference it.

- The independence definition gates the risk-committee rule and the audit-committee consolidation; it starts in Phase 2 because SEC coordination is the longest pole.

- Vertical rationalization (Phase 4) depends on the consolidated risk-committee standard, the risk-appetite template, and the enterprise-framework statement being in force.

- Two principals' values are prerequisites inside Phase 2–3 items: the critical-activity threshold (third-party) and the incident-notification timeline (info-security).

- Retained and non-target items (Reg O, consumer compliance, BSA program substance, personal liability, source-of-strength) have no implementation action by design.